Scope of Work Nexus Development Support Draft for JT review and cost confirmation

| Prepared for | JT Somwaru |
| --- | --- |
| Prepared by | MSI The Agency/Ed Clarke |
| Engagement owner | Samantha Foy |
| Technical lead | Ed Clarke |
| Proposed duration | 4 weeks |
| Proposed effort | Up to 80 hours, based on 20 hours per week |
| Status | Draft for scope, rate, and cost confirmation |

This document defines the proposed work, assumptions, dependencies, governance, and commercial placeholders for a short-term contractor/freelancer engagement. It is intended to help JT review the expected scope and confirm his rate and total estimated cost before MSI finalizes the engagement.

# 1. Background and objectives

MSI Intelligence Nexus is MSI’s internal analytics platform supporting client performance dashboards, AI-assisted reporting, and operational tooling. Current development capacity is the constraint on how quickly MSI can onboard clients and build repeatable platform capabilities.

This proposed engagement adds short-term development capacity in two priority areas: reusable platform tooling that accelerates future client-dashboard builds, and two new internal client dashboards built on the standard Nexus architecture. Ed Clarke will continue to lead the platform and a separate set of parallel workstreams; those items are excluded from this scope and noted only for coordination.

| Objective 1 | Objective 2 | Objective 3 |
| --- | --- | --- |
| Build reusable tooling that makes client-dashboard onboarding faster, more consistent, and easier to maintain. | Stand up two new client dashboards on the standard Nexus architecture: NJ Lottery and Montclair. | Execute within the platform’s engineering, review, testing, and security discipline so work is auditable and production-ready. |

2. Engagement summary

| Item | Detail |
| --- | --- |
| Resource | JT, part-time developer/contractor candidate |
| Availability | 20 hours per week |
| Duration | 4 weeks |
| Total estimated effort | 80 hours |
| Oversight | Ed Clarke, technical lead; Samantha Foy, budget and engagement owner |
| Engagement type | Contractor or fractional role, to be finalized by MSI |
| Primary purpose | Increase Nexus development capacity while evaluating fit, quality, and working model |

Why the tooling comes first: The Dashboard Creation Playbook agent is intentionally sequenced before the dashboards. Automating the repeatable parts of onboarding should make NJ Lottery faster and Montclair faster still. Building the accelerator first is what keeps the two dashboard builds within the proposed 80-hour envelope.

# 3. Scope of work

The engagement includes a short onboarding/ramp period and four scoped deliverables. Hour estimates are planning ranges. The tooling items carry more uncertainty because they involve higher-judgment platform work and overlap with ramp-up.

## Deliverable 0: Onboarding and ramp

Estimated effort: Approximately 6 hours, Week 1

Environment setup and orientation before production work begins. JT will be provisioned with the required access and will learn the Nexus working discipline through low-risk exercises.

Key tasks

Provision access: Entra ID account, scoped Snowflake dev role, Azure DevOps repo access, local development environment, Claude Code, and the Nexus plugin.

Review core platform documentation, including CLAUDE.md lessons, the Dashboard Creation Playbook, and the Code Modification Protocol.

Run one read-only data probe end to end and complete one supervised targeted edit to learn the read, state, apply, dev-test, and diff-review gates.

Acceptance criteria

JT can authenticate, query Snowflake under a scoped dev role, run the app locally, and complete the approved read to state to apply to dev-test flow on a low-risk change.

## Deliverable 1: Dashboard Creation Playbook agent

Estimated effort: Approximately 20 hours

A reusable tool that automates repeatable new-client dashboard onboarding steps from the standard template, making onboarding primarily configuration-based instead of fully manual.

Key tasks

Automate the onboarding checklist: read-only data probe scaffold, client registry entry, fiscal configuration, route wiring, and client-health panel branch.

Accept a client configuration as input and generate a working dashboard skeleton with shell, standard sections, and standard wiring.

Flag items that require human judgment, including metric definitions, channel taxonomy, and data-source mapping, rather than fabricating assumptions.

Package the agent through the Nexus plugin so it is available to the team and not tied to a single developer machine.

Acceptance criteria

Produces a correct client dashboard skeleton from configuration.

Does not write to shared database tables without an explicit approval gate.

Is proven through use on the two dashboard builds included in this scope.

## Deliverable 2: NJ Lottery dashboard

Estimated effort: Approximately 22 hours

A performance dashboard for NJ Lottery on the standard Nexus architecture and the first production-style use of the Playbook agent. As the first client build in this scope, it is expected to run slower because data must be profiled and mapped before dashboard sections can be built.

Key tasks

Run the Phase 0 data probe to confirm which sections are feasible from available data.

Stand up the data foundation, including schema, media data wiring, channel taxonomy, and mapping logic.

Build standard sections, including Executive Summary and Media Performance where supported by the data.

Seed triggers, wire AI insight cards, and validate cross-tab consistency and fiscal handling.

Acceptance criteria

Dashboard passes internal dev-test.

Numbers reconcile across tabs; aggregates are weighted correctly; fiscal periods are correct for the client.

Dashboard remains internal only; no external client credential is provisioned as part of this scope.

## Deliverable 3: QA agent

Estimated effort: Approximately 16 hours

An automated validation agent that guards against the error classes that matter most for Nexus: calculation errors, data-source errors, and silent failures. The agent will run on demand and report issues before work is pushed forward.

Key tasks

Cross-tab agreement: flag when the same metric disagrees across dashboard surfaces.

Aggregate correctness: catch average-of-ratios issues and other weighted-aggregate violations.

Data freshness and volume: alert on stale sources and abnormal load volumes.

Silent-failure detection: distinguish a real database result from a fallback value that fired quietly.

Package the agent through the Nexus plugin and wire it to run on demand before a push.

Acceptance criteria

Catches a seeded calculation error, a cross-tab mismatch, and a stale or fallback-masked value.

Never asserts a data fact it did not verify; fails loud rather than passing silently.

Runs against the new dashboards and existing production clients.

## Deliverable 4: Montclair dashboard

Estimated effort: Approximately 16 hours

A second client performance dashboard, expected to be materially faster than NJ Lottery because the Playbook agent will already exist and JT will have completed one full client build.

Key tasks

Run the Phase 0 probe, generate the dashboard skeleton with the Playbook agent, and build the client-appropriate sections.

Seed triggers and AI insights.

Validate cross-tab consistency, weighted aggregates, and fiscal handling.

Acceptance criteria

Dashboard passes internal dev-test with cross-tab consistency and correct aggregates.

Build time is materially shorter than NJ Lottery, demonstrating the value of the Playbook agent.

# 4. Proposed four-week schedule

The schedule is accelerator-first: the Playbook agent is built before the dashboards so the two client builds can remain within the proposed hour budget.

| Week | Primary focus | Hours |
| --- | --- | --- |
| Week 1 | Onboarding and ramp; begin Dashboard Creation Playbook agent | 20 |
| Week 2 | Finish Playbook agent; begin NJ Lottery dashboard | 20 |
| Week 3 | Finish NJ Lottery dashboard; begin QA agent | 20 |
| Week 4 | Finish QA agent; build Montclair dashboard | 20 |
| Total | Four-week engagement | 80 |

# 5. Out of scope

External client credential provisioning. Nexus remains internal for this work. Opening the platform to an external client requires separate authentication middleware approval and David Lemus security sign-off.

Ed Clarke’s parallel workstreams, including internal scope-tracking reporting and the executive dashboard. These are noted for coordination only and are not part of JT’s delivery scope.

Any work dependent on pending Anthropic or Advantage API keys, including Creative Analyzer vision features, until those keys are provisioned and approved for use.

Production deployment, external launch, or client-facing release activity unless separately approved by MSI.

Additional client dashboards, new platform features, or material changes to the standard Nexus architecture outside the deliverables listed above.

6. Assumptions and dependencies

| Dependency | Assumption / Requirement |
| --- | --- |
| Access readiness | Access must be provisioned before Week 1 work begins, including Entra ID, Nexus app-registration access, Snowflake scoped dev role, Azure DevOps repo access, local development environment, Claude Code, and the Nexus plugin. |
| Least-privilege access | JT will use a personal Snowflake user with a scoped dev role. Access should not include ACCOUNTADMIN privileges or the production service account. |
| Data readiness | NJ Lottery and Montclair source data must be reachable in Snowflake. Each dashboard begins with a read-only probe. If a probe shows data is blocked, that item’s schedule shifts and effort is rebalanced to the other deliverables. |
| Shared tooling | Agents created under this scope will be packaged and distributed through the Nexus plugin so the tooling is available to the broader team. |
| Fixed effort envelope | The scope is calibrated to 80 hours across four weeks. If onboarding takes longer than expected or a data probe blocks a dashboard, the Montclair build is the flex item and may move to a follow-on scope. |

# 7. Roles and responsibilities

| Person | Role on this engagement |
| --- | --- |
| JT | Delivers the scoped items and runs Claude Code against the repo within the platform’s approved gates. |
| Ed Clarke | Technical lead. Authors prompts during ramp, verifies work at dev-test and diff-review gates, owns the shared shell, and coordinates with parallel workstreams. |
| Samantha Foy | Budget and engagement owner. Confirms engagement type, approves final scope, and reviews commercial terms. |
| Dave Milillo | Supports Snowflake access and data engineering needs. |
| Madhuri | Supports Azure and DevOps access provisioning. |
| David Lemus | Provides security sign-off for any later external-facing step. |

# 8. Ways of working and governance

All work must follow the Nexus Code Modification Protocol: read the current file, state the exact intended change, apply the change, test locally at the dev-test gate, and build or deploy only after approval. Runtime code requires full local testing and build validation. Documentation and configuration changes require diff review.

Commit discipline: stage explicit named paths only; no bulk staging.

File ownership: JT focuses on new tooling and new-client files; Ed owns the shared shell and parallel internal workstreams.

Coordination: pushes are sequenced and no two sessions edit the same file at the same time.

Quality gates: no work reaches production untested or unreviewed.

Security boundary: no external client credential is issued during this engagement.

Weekly checkpoint: MSI and JT will review progress, blockers, remaining hours, and any scope decisions at least once per week.

# 9. Change control

Any material change to deliverables, priority, timing, access requirements, or expected effort must be approved by Samantha Foy and Ed Clarke before work proceeds. If a blocker changes the scope materially, MSI will either rebalance the remaining hours inside the 80-hour envelope or document a follow-on scope for separate approval.

# 10. Commercial summary

Commercial terms are intentionally left open for JT and MSI to confirm. JT should review this scope and provide his hourly rate, total estimated cost, and any assumptions or exclusions that may affect delivery.

| Item | Value |
| --- | --- |
| Total estimated effort | 80 hours |
| Cadence | 20 hours per week |
| Duration | 4 weeks |
| Hourly rate | [To be confirmed by JT] |
| Estimated budget | [80 hours x confirmed hourly rate] |
| Engagement type | Contractor |
| Billing cadence | [To be confirmed] |
| Start date | [To be confirmed] |

# 11. Items to confirm before kickoff

| Confirmation item | Owner |
| --- | --- |
| JT confirms hourly rate, availability, and any delivery assumptions. | JT |
| MSI confirms engagement type, start date, billing cadence, and any contractor agreement requirements. | Samantha Foy / MSI |
| Access provisioning is complete before production work begins. | Madhuri / Dave Milillo / Ed Clarke |
| Security expectations, confidentiality, IP ownership, and external-access restrictions are addressed in the final contractor agreement. | MSI / Legal or authorized reviewer |

Prepared as a working scope for contractor review and cost confirmation. Final engagement terms are subject to MSI approval and any required contractor agreement.